## About (hidden)
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | STRATEGIC THEME TITLE | [8 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Executive Sponsors: Lana Poole, Marty Loy | [8 empty] | Goal |  |  |  |  | Outcome |  |  |  |  | Strategy |  |  |  |  | Metric
pw:UWSPstratplan
Implementation Co-Chairs: Laura Bell, Brad Duckworth
Implementation Team: Lisa Michalec, Ricarod Boeing, Peter Zuge, Ann Herda-Rapp
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  |  |  | Project Start Date: |  | 2021-07-01 |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4 | [11 empty] | YEAR 5
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. | [9 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-07-01 to 2026-06-01
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Purpose Made Possible Goal | Responsible Division | Category | Assigned To | Progress | Start | No. Days | Resource Needs | time axis 2021-07-01 to 2026-06-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. Sample data is in cells B9 through G33. Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting. The next instruction is in cell A34. | Goal | We will increase and expand access by enhancing strategic partnerships with high schools and other educational institutions that support college-bound student success, college completion, and enrollment growth for a diverse student body. | Marketing & Enrollment | Goal | Lana Poole, Laura Bell, Director of Admissions |  | 2021-07-01 | 730
| Outcome/Strategy/Metric | Develop five-year recruitment and enrollment targets by student segment by July 2022 (dependent upon AA program expansion decisions) (e.g. UGRD, TRAN, URM, INTL, Out-of-State, MSEP, Honors, Adult, First-Gen) | Marketing & Enrollment | Outcome | Lana Poole, Marty Loy, Katie Jore, Laura Bell | short-term goals set, need to comlpete 5-year | 2021-07-01 | 180 | NONE
| Outcome/Strategy/Metric | Analyze demographic and market trends, historical enrollments, and new program potential to create new pipelines, benchmarks and predictive models. | Marketing & Enrollment | Strategy |  |  | 2022-07-01 | 180 | NONE
| Outcome/Strategy/Metric | Metric/measure will be number of students in each enrollment segment as noted above | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 180
| Outcome/Strategy/Metric | Optimize the use of marketing tools and strategies to achieve recruitment and enrollment targets. | Marketing & Enrollment | Outcome | Chris Brundidge and Brittany Kaminski | Evaluating budget alignment with technology needs (nearly complete) | 2021-07-01 | 360 | SEE BELOW
| Outcome/Strategy/Metric | Implement SEO strategies and utilize data analytics to increase prospective student website traffic and engagement by establishing benchmarks at January, 2022 launch. | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 210 | SEM RUSH
| Outcome/Strategy/Metric | Metric/measure will be traffic, engagement and conversions with benchmarks established at launch of website. | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 210
| Outcome/Strategy/Metric | Utilize a concentrated omni-channel marketing strategy (e.g. email, postal mail, social media, URL address, and text) to engage best-fit prospect and inquiry student segments | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 360 | FUTURE YEARS FUNDING
| Outcome/Strategy/Metric | Metric/measure will be leads generated through digital ads, website, and other tactics to increase historical number by 10% by July 2022 (from 8,800 to 9,680) | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 360
| Outcome/Strategy/Metric | Implement and optimize use of new CRM tool to build relationships with prospective students | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 360 | $52K-82K NAME-BUYING IN FUTURE YEARS
| Outcome/Strategy/Metric | Metric/measure will be ability to engage prospects and inquiries via open rates, click-through rates, unsubscribe rates, response rates, movement through funnel, etc. - benchmarks established July 2021 when Slate is launched | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 360
| Outcome/Strategy/Metric | Optimize Available Scholarship and Grant Dollars to support every segment (e.g. UGRD, TRAN, URM, INTL, Out-of-State, MSEP, Honors, Adult, First-Gen) | Marketing & Enrollment | Outcome | Lana Poole, Laura Bell, Mandy Slowinski/Elspeth, foundation, branch, academic affairs, admissions staff | Evaluating strategies, workign with foundation/branch/AA/admissions | 2021-07-01 | 730 | ACADEMIC WORKS/SOFTWARE NEEDS
| Outcome/Strategy/Metric | Ensure that 100% of WI Grant dollars are awarded annually | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 210 | NONE
| Outcome/Strategy/Metric | % of WI Grant dollars awarded | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 210
| Outcome/Strategy/Metric | Decrease number of students that remain in Financial Aid verification process by 10% by removing barriers, in particular for URM and first-gen students, by September, 2022 | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 3602 | VENDOR HELP IF VERIFICATION CONTINUES
| Outcome/Strategy/Metric | Metric/measure is number of students processed through verification | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 360
| Outcome/Strategy/Metric | Using fall 2021 as a benchmark, increase yield rate from admit to enroll by 5% by fall 2022 | Marketing & Enrollment | Outcome | Director of Admissions, Lana Poole, Laura Bell | Yielding plan is being executed, search for new director | 2021-07-01 | 360 | SEE BELOW
| Outcome/Strategy/Metric | Strategies, goals, and timeline will be established as we launch new engagement tools (e.g. SEM Rush, ZeeMee, parent tool), establishment of customer service center, and launch of new CRM system | Marketing & Enrollment |  |  |  |  | 360 | SCHOLARSHIP DOLLARS AND FUTURE YEARS FUNDING
Outcome/Strategy/Metric
Outcome/Strategy/Metric
Outcome/Strategy/Metric
Outcome/Strategy/Metric
Outcome/Strategy/Metric
Outcome/Strategy/Metric
| Outcome/Strategy/Metric | Increase high school campus visit numbers by 38% by fall 2022 | Marketing & Enrollment | Outcome | Rachel Siebers in conjunction with Chris Brundidge, academic units, athletics, and recruiters | In progress | 2021-07-01 | 360 | TBD
| Outcome/Strategy/Metric | Develop, in partnership with academic departments, new on-campus visit experiences to feed high-demand programs by fall 2023 (major days, career days, competitions/tournaments, etc.) | Marketing & Enrollment | Strategy |  |  | 2021-07-01 | 360 | TBD
| Outcome/Strategy/Metric | Goals and metrics based on enrollment goals following budget | Marketing & Enrollment | Metric |  |  | 2021-07-01 | 360
| Outcome/Strategy/Metric | Increase students who articulate from WTCS institutions by May 2023. | Academic Affairs | Outcome | Todd Huspeni | In progress | 2021-07-01 | 730 | TBD
| Outcome/Strategy/Metric | Complete ongoing grant-funded project to develop a master UW System transfer agreement for the liberal arts WTCS degree. | Academic Affairs |  |  |  | 2021-07-01 | 365 | TBD
| Outcome/Strategy/Metric | Extend existing UWSP articulation agreements to other Wisconsin Technical College System institutions. | Academic Affairs |  |  |  | 2021-07-01 | 730 | TBD
| Outcome/Strategy/Metric | Explore offering needed degree-completion programs online to expand access to place-bound, working students. | Academic Affairs |  |  |  | 2021-07-01 | 730 | TBD
| Goal | We will grow programs and harness technologies to support post-traditional and graduate learners through creative delivery methods including but not limited to branch campuses, hybrid, online, or collaborative models. This shall involve strengthening student support in terms of course timing/availability, academic calendars, evening/weekend classroom, office and service access, and prior learning experience. | Academic Affairs | Goal
| Outcome/Strategy/Metric | Create a multifaceted credit for prior learning structure by May 2022. | Academic Affairs | Outcome | Todd Huspeni | In progress
| Outcome/Strategy/Metric | Work with schools to evaluate which disciplines are most appropriate for prior learning. | Academic Affairs |  |  |  | 2021-07-01 | 300 | STAFF TIME/ENGAGEMENT
| Outcome/Strategy/Metric | Evaluate competitive landscape to understand how technical, private, and UW schools structure credit for prior learning. | Academic Affairs |  |  |  | 2021-07-01 | 300 | STAFF TIME/ENGAGEMENT
| Outcome/Strategy/Metric | Create a structure to develop online programs to serve targeted needs, support multiple online delivery methods, and support students in online programs. | Academic Affairs | Outcome | Marty Loy | Proposal near complete | 2021-07-01 | 365 | SEE BELOW
| Outcome/Strategy/Metric | Develop options for an administrative structure to support online programs. | Academic Affairs | Outcome |  |  | 2021-07-01 | 180 | UTILIZE DE FEE TO SUPPORT
| Outcome/Strategy/Metric | Evaluate the program areas and student segments for which there is a market demand for online offerings. | Academic Affairs | Outcome |  |  | 2021-07-01 | 365
| Outcome/Strategy/Metric | Develop a pipeline of new online programs targeted to post-traditional students by XXXX. | Academic Affairs | Outcome |  |  | 2021-07-01 | 365
| Outcome/Strategy/Metric | Purposefully develop online programs to serve traditional and technical college transfer students. | Academic Affairs | Outcome |  |  | 2021-07-01 | 365
| Goal | We will develop and implement internal systems and structures to better serve diverse prospective students in our market. The system should use data to determine financial and program viability, and inform new programs/offerings relevant to K-12 traditional, post-traditional, graduate, and continuing ed students. | Academic Affairs | Goal
| Outcome/Strategy/Metric | Create a regular process supporting new program development, including majors, certificates, and “stackable” academic credentials, in partnership with the Division of Marketing and Enrollment by May 2022. | Academic Affairs | Outcome | Marty Loy | Proposal near complete | 2021-07-01 | 365 | SEE BELOW
| Outcome/Strategy/Metric | Expand and evaluate the use of Burning Glass for market research and career outcome data. | Academic Affairs |  |  |  | 2021-07-01 | 180 | FUTURE YEARS FUNDING
| Outcome/Strategy/Metric | Annually scan for program development opportunities best able to reach traditional and post-traditional students, noting best options to improve access through instructional modality or campus location. | Academic Affairs |  |  |  | 2021-07-01 | 365 | TBD
| Outcome/Strategy/Metric | Formalize the rigorous evaluation of market demand, instructional capacity, and other financial requirements for all proposed programs. | Academic Affairs |  |  |  | 2021-07-01 | 60 | EST. YEAR 1 $33,000; YEAR 2 AND BEYOND $66,000; CONSIDER STRATEGIC INVESTMENT FUND
| Outcome/Strategy/Metric | Provide an annual program health report with key performance indicators for all undergraduate and graduate programs by May 2022. | Academic Affairs | Outcome | Todd Huspeni, Katie Jore, Lana Poole | Discussion begins January 28 | 2021-07-01 | 365 | STAFF TIME/ENGAGEMENT
| Goal | We will increase our unique cross-disciplinary work to leverage (or promote) our strengths in sustainability, global awareness, and diversity, equity, and inclusion, for prospective students at all credential and continuing education levels. | Academic Affairs | Goal
| Outcome/Strategy/Metric | Community Sustainability major will be launched by Fall 2022 | Academic Affairs | Outcome |  | Completed | 2021-07-01 | 180 | NONE
This row marks the end of the Gantt milestone data. DO NOT enter anything in this row. To add more items, insert new rows above this one. | To add new data, insert rows ABOVE this one

## PMP Goal Organization
Purpose Made Possible Goals
We will align University expenditure levels with available resources. Annual expenditure levels in university departments will be within the annual state budget allocation or the program revenue generated. | Finance 1.1
We will utilize financial models that will be data informed, transparent, objective, and action oriented. The financial models will inform decisions to allocate and reallocate resources. | Finance 1.2
We will create ethical processes and metrics to support the financial models and to inform decision-making, resulting in greater transparency and understanding of the current financial situation of the university, the rationale for decision making, and the need to ensure long-term financial sustainability. | Finance 1.3
We will encourage and achieve financial growth. New revenue sources will be explored and analyzed for financial viability. These new revenue sources will complement existing financial resources to allow diversification of university finances. | Finance 1.4
We will increase and expand access by enhancing strategic partnerships with high schools and other educational institutions that support college-bound student success, college completion, and enrollment growth for a diverse student body. | Student Success 1.1
We will grow programs and harness technologies to support post-traditional and graduate learners through creative delivery methods including but not limited to branch campuses, hybrid, online, or collaborative models. This shall involve strengthening student support in terms of course timing/availability, academic calendars, evening/weekend classroom, office and service access, and prior learning experience. | Student Success 1.2
We will develop and implement internal systems and structures to better serve diverse prospective students in our market. The system should use data to determine financial and program viability, and inform new programs/offerings relevant to K-12 traditional, post-traditional, graduate, and continuing ed students. | Student Success 1.3
We will increase our unique cross-disciplinary work to leverage (or promote) our strengths in sustainability, global awareness, and diversity, equity, and inclusion, for prospective students at all credential and continuing education levels. | Student Success 1.4
We will prioritize and expand high-impact practices (HIP) to boost student learning, development, and engagement. | Student Experience 1.1
We will deliver vibrant yet tailored student services that support the retention and success of all students. | Student Experience 1.2
We will build and enhance a community that values inclusion, equity, and diversity. | Student Experience 1.3
We will create an enriched learning environment through the use of advanced evidence-based practices and educational tools, innovative technologies, and equity-minded pedagogies. | Student Experience 1.4
We will collaborate both internally and with community members and organizations to create initiatives that support economic and community development. We will share our stories with each other and our stakeholders and work together to enhance our community. | Communities 1.1
In our internal and external collaborations we will focus on our commitment to be more inclusive and promote equity and diversity. | Communities 1.2
As an educational and cultural resource for the communities we serve, we will develop and promote new types of collaborations that align with the mission of UW-Stevens Point and that lead to greater efficiency, greater opportunity for a UWSP credential, and greater student success through internships and other experiential learning. | Communities 1.3

## Sheet1 (hidden)
FY22 | Executive
FY23 | Advancement
FY24 | Marketing & Enrollment
FY25 | Student Affairs
FY26 | Business Affairs
Academic Affairs