## About (hidden)
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. A scroll bar allows you to scroll through the timeline. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with hidden text. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. This hidden text will not print. To remove these instructions from the worksheet, simply delete column A.
This is the last instruction in this worksheet.

## Gantt
Create a Gantt Chart in this worksheet. Enter title of this project in cell B1. Legend title is in cell I1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. | Student Affairs Strategic Plan | [8 empty] | Legend:
Enter Company Name in cell B2. A legend is in cells I2 through AC2. | Executive Sponsor: Al Thompson, Vice Chancellor for Student Affairs | [8 empty] | Goal |  |  |  |  | Outcome |  |  |  |  | Strategy |  |  |  |  | Metric
pw:UWSPstratplan
Strategic Planning Chairperson: Laura Ketchum-Ciftci
Strategic Planning Team: Suzette Conley, Brad Duckworth, Stacey Gerken, Troy Seppelt
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell F3 or allow the sample formula to find the smallest date value from the Gantt Data table. Project Start Date: label is in cell D3. |  |  |  |  | Project Start Date: |  | 2021-07-01 |  |  | YEAR 1 | [11 empty] | YEAR 2 | [11 empty] | YEAR 3 | [11 empty] | YEAR 4 | [11 empty] | YEAR 5
A Scrolling Increment is in cell F4. Months for the dates in row 5 are displayed starting in cells I4 through cell BL4. Do not modify these cells. They are auto updated based on the project start date in cell F3. | [9 empty] | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
Cells I5 through BL5 contain the day number of the month for the Month represented in the cell block above each date cell and are auto calculated. Do not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2021-07-01 to 2026-06-01
This row contains headers for the project schedule that follows below them. Navigate from B7 through BL7 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I7 and continues through cell BL7. All project timeline charting is auto generated based on the category, start date and number of days entered in the Milestones table. | Milestone Description | Student Affairs Goal (Purpose Made Possible) | Responsible Division(s) | Category | Assigned To | Progress | Start | No. Days | Resource Needs | time axis 2021-07-01 to 2026-06-01
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Enter Project information starting in cell B9 through cell G9. | We will prioritize and expand high-impact practices (HIP) to boost student learning, development, and engagement. | 1.0 High Impact Practices (Student Experience 1.1) |  | Goal
Sample data is in cells B9 through G33.
Enter Milestone Description, select a Category from the drop-down list, assign someone to the item, enter the progress, start date and number of days for the task to start charting.
The next instruction is in cell A34.
| Focus efforts on equitable student access to HIPs we can do well as an institution and for which we can demonstrate markers of quality, ensuring that all students participate in at least two HIPs during their college career, with at least one taking place during their first year on campus. | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) |  | Outcome |  |  | 2022-01-01 | 1825
| Develop a shared understanding of markers of quality and a rubric for assessing existing and new high impact practices. | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) | Academic Affairs / Student Affairs | Strategy | SAAT Chair & CITL Faculty Fellow | Waiting on Faculty Fellow assignement | 2022-01-01 | 365 | Staff Time and Assessment Money | bar: 2021-07-01 to 2022-06-01
| Rubric adopted by May 2022 for implementation in fall 2022 | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) | Academic Affairs / Student Affairs | Metric |  |  |  |  | Staff Time and Assessment Money
| Educate all student affairs staff of the benefits of High Impact Practices for recruitment, retention and overall student success and engagement | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) | Student Affairs | Strategy
| Enhance Learning Community options within residence halls and for commuter and post-traditional students. | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) | Student Affairs | Strategy
| Create a High Impact Practice student employment program that all students can participate in regardless of their intended career path or major. | 1.1 High Impact Practices - Equitable Access (Student Experience 1.1) | Student Affairs | Strategy
| Explore new and enhance existing Academic Affairs/Student Affairs program partnerships that develop student learning and engagement. | 1.2 High Impact Practices - Partnerships (Student Experience 1.1) | Student Affairs | Outcome |  |  | 2021-07-01 | 1825
| Increase internships/capstone placements across all Student Affairs departments – childcare, graphic design and marketing, residential living, culinary arts, etc. | 1.2 High Impact Practices - Partnerships (Student Experience 1.1) | Student Affairs | Strategy | VCSA/SA Departmental Directors |  | 2022-01-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Number of students participating in internships/capstone placements in Student Affairs departments | 1.2 High Impact Practices - Partnerships (Student Experience 1.1) | Student Affairs | Metric | VCSA/SA Departmental Directors |  |  |  | Staff Time
| Evaluate a collaborative Health and Wellness program across campus for high impact outcomes. | 1.2 High Impact Practices - Partnerships (Student Experience 1.1) | Student Affairs | Strategy | VCSA/ Health and Wellness Directors |  | 2022-07-01 | 1460 | bar: 2022-07-01 to 2026-06-01
| We will deliver vibrant yet tailored student services that support the retention and success of all students. | 2.0 Vibrant/Tailored Student Services (Student Experience 1.2) |  | Goal
| Achieve and maintain a minimum annual first-to-second year retention rate of 80%. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) |  | Outcome |  |  | 2021-07-01 | 1825
| Identify and scale up successful retention initiatives within Student Affairs. Improve coordination, collaboration, and communication around retention and student success. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Student Affairs | Strategy | VCSA/SA Departmental Directors |  | 2022-01-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Initiatives are identified and revised by May 2022 for implementation in fall 2022 | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Student Affairs | Metric | VCSA/SA Departmental Directors |  |  |  | Staff Time
| Identify high DFW courses with departments and recommend changes. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2021-01-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
Course list and recommendations submitted to academic units by December 2021 | List of courses and recommendations submitted to academic units by May 2022 | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee |  |  |  | Staff Time
| Partner with degree-granting colleges, programs, and constituent groups to develop retention targets for programs and student segments. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2021-10-01 | 365 | bar: 2021-07-01 to 2022-06-01
| Retention targets communicated to programs by December 2021 | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Work with Navigate teams and other tools to integrate and communicate support for first-year students intentionally and strategically in the curriculum, co-curriculum, student support, and financial operations. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-03-01 | 730 | Staff Time | bar: 2021-07-01 to 2023-06-01
| Creation and use of a tracking mechanism to manage student communication across units | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee |  |  |  | Staff Time
| Investigate and suggest strategies to address the root causes of attrition to the technical colleges in the first year. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-01-01 | 365 | bar: 2021-07-01 to 2022-06-01
| Submit strategies to Academic Affairs and Student Affairs by December 2021 | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Increase the number of students with mid-semester balances who can enroll in subsequent semesters by leveraging institutional and retention strategies. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Reduce the number/percentage of holds due to mid-semester balances by ? | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee |  |  |  | Staff Time
| Encourage development of intentional meta-major pathways for undeclared students, including curricular and co-curricular programming. | 2.1 Vibrant/Tailored Student Services - Retention (Student Experience 1.2) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee
| Develop an intentional plan to increase student engagement to foster a “Sense of Belonging” for all UWSP Students | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) |  | Outcome |  |  | 2021-07-01
| Grow SPIN usage by Student Affairs departments and UWSP students by 15% to cultivate increased student engagement. | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Strategy | University Centers/ CASE | Begun Marketing, Monthly Tracking | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| 15% Increase in usage of SPIN 15% by May 2022 to better understand student engagement and which students appear not to be engaged | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Metric | University Centers/ CASE |  |  |  | Staff Time
| Enhance student service support to the branch campuses | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Strategy | VCSA / SA Departmental Directors |  | 2022-01-01 | 365 | Staff Time and Money | bar: 2021-07-01 to 2022-06-01
| Identify specific support services for enhancement by May 2022 and implement in fall 2022 | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Metric | VCSA / SA Departmental Directors |  |  |  | Staff Time and Money
| Develop and implement intentional interventions to increase equitable participation in student engagement activities (vets, commuter, on-line students, underserved, and underrepresented students) | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Strategy
| Develop and expand programs to support first-year transition. | 2.2 Vibrant/Tailored Student Services - Sense of Belonging (Student Experience 1.2) | Student Affairs | Strategy
| We will build and enhance a community that values Diversity, Equity, and Inclusion. | 3.0 Diversity, Equity, and Inclusion (Student Experience 1.3) |  | Goal
| Achieve a 10% increase in first-to-second year retention of students of color by 2025. | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Outcome |  |  | 2021-07-01 | 1825
| Create a team of faculty, staff and students who are experts in their areas to draft a plan on addressing closing the achievement gap. | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Strategy | Academic Affairs / Student Affairs / Retention Steering Committee |  | 2022-01-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Team created by fall 2021 and plan completed by May 2022 | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Metric | Academic Affairs / Student Affairs / Retention Steering Committee |  |  |  | Staff Time
| Identify through exit interviews, case-load model student-advisor engagement, and other tactics the reasons why students of color leave and stay at UWSP. | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Strategy | Academic Affairs / Student Affairs / Retention Steering Committee |  | 2022-01-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| List of reasons submitted to Academic Affairs and Student Affairs by May 2022 | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Metric | Academic Affairs / Student Affairs / Retention Steering Committee |  |  |  | Staff Time
| Identify specific students who are “at risk” by subgroup and mitigate attrition by providing specific, evidence-based interventions. | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Strategy | Academic Affairs / Student Affairs / Retention Steering Committee |  | 2022-07-01 | 365 | bar: 2022-07-01 to 2023-06-01
| Students are identified by December 2022 and interventions implemented in spring 2023 | 3.1 Diversity, Equity, and Inclusion - Retention (Student Experience 1.3) |  | Metric | Academic Affairs / Student Affairs / Retention Steering Committee
| Ensure that UWSP provides opportunities for high quality engagement with social justice content to all students, faculty, staff, and community members by fall 2023. | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) |  | Outcome |  |  | 2021-07-01 | 730 | bar: 2021-07-01 to 2023-06-01
| Develop a social justice institute that examines the root cause of social injustice and helps to develop innovative solutions. | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) | Academic Affairs / Student Affairs | Strategy | VCSA/CDO & CITL Director | Done | 2021-07-01 | 730 | Staff Time/ Faculty Fellow | bar: 2021-07-01 to 2023-06-01
| Proposal completed by May 2022 for review and implementation during 2022-2023 | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) | Academic Affairs / Student Affairs | Metric | VCSA/CDO & CITL Director | Done |  |  | Staff Time/ Faculty Fellow
| Collaborate with Academic Affairs (CITL) to provide enhanced inclusivity and cultural competency trainings. | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) | Academic Affairs / Student Affairs | Strategy | VCSA/CDO & CITL Director | proposal completed, implementation being worked on | 2021-07-01 | 730 | Staff Time/ Faculty Fellow | bar: 2021-07-01 to 2023-06-01
| Enhanced training program developed by May 2022 for implementation starting in fall 2022 | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) | Academic Affairs / Student Affairs | Metric | VCSA/CDO & CITL Director | Begun | 2021-07-01 |  | Staff Time/ Faculty Fellow
| Investigate the creation of a Social Justice Leadership Collective or Camp for students once the SJI is established (3-level on-line training module suggested) | 3.2 Diversity, Equity, and Inclusion - Social Justice (Student Experience 1.3) | Student Affairs | Strategy
| Evaluate and reward contributions to DEI work by faculty and academic staff by fall 2023. | 3.3 Diversity, Equity, and Inclusion - Reward Work (Student Experience 1.3) |  | Outcome |  |  | 2021-07-01 | 730 | bar: 2021-07-01 to 2023-06-01
| Make contributions toward EDI a mandatory metric for all annual personnel (P&T, merit, etc.) and program reviews, and hold people accountable when no progress is made. | 3.3 Diversity, Equity, and Inclusion - Reward Work (Student Experience 1.3) | Business Affairs | Strategy | University Wide |  | 2021-07-01 | 730 | Staff Time | bar: 2021-07-01 to 2023-06-01
| Revise review process by December 2021 for implementation in 2022 | 3.3 Diversity, Equity, and Inclusion - Reward Work (Student Experience 1.3) | Business Affairs | Metric | University Wide |  |  |  | Staff Time
| Improve recruitment and retention of underrepresented academic staff. | 3.4 Diversity, Equity, and Inclusion - Recruitment/Retention (Student Experience 1.3) |  | Outcome |  |  | 2021-07-01 | 1825
| Develop a formalized mentor program to encourage and support the development of current undergraduate and graduate students of color at UWSP to become future UWSP full-time staff members | 3.4 Diversity, Equity, and Inclusion - Recruitment/Retention (Student Experience 1.3) | Student Affairs | Strategy | Student Affairs / Business Affairs
| Begin mandatory on-line cultural competency trainings for all staff | 3.4 Diversity, Equity, and Inclusion - Recruitment/Retention (Student Experience 1.3) | Student Affairs | Strategy | Student Affairs / Academic Affairs (CITL)
Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | We will create an enriched learning environment through the use of advanced evidence-based practices and educational tools, innovative technologies, and equity-minded pedagogies. | 4.0 Learning Environment (Student Experience 1.4) |  | Goal
| Address curricular barriers to student success in their first two years. | 4.1 Learning Environment - Curricular Barriers Mitigated (Student Experience 1.4) |  | Outcome | Retention Steering Committee |  | 2021-07-01 | 1825
| Develop a proposal for mandatory mid-term grade reporting and present it as a policy to Academic Affairs Committee. | 4.1 Learning Environment - Curricular Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2021-09-01 | 330 | bar: 2021-07-01 to 2022-05-01
| Proposal submitted by December 2021 | 4.1 Learning Environment - Curricular Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Address administrative barriers to student success in the first two years. | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) |  | Outcome | Retention Steering Committee |  | 1/12022 | 1825
| Conduct a barrier audit on student personas to identify what inhibits retention. | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-01-01 | 365 | bar: 2021-07-01 to 2022-06-01
| Barrier audit submitted by May 2022 | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Investigate waitlist practices and make recommendations for changes in campus processes. | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-07-01 | 330 | bar: 2022-07-01 to 2023-05-01
| Recommendations submitted by May 2023 | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Conduct an audit on holds that inhibit registration to determine their necessity and impact. | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Strategy | Retention Steering Committee |  | 2022-01-01 | 365 | bar: 2021-07-01 to 2022-06-01
| Report submitted by May 2022 | 4.2 Learning Environment - Administrative Barriers Mitigated (Student Experience 1.4) | Academic Affairs w/ SA Representation | Metric | Retention Steering Committee
| Develop a core set of intentional learning outcomes and programs to promote student development within Student Affairs programs and services. | 4.3 Learning Environment - Learning Outcomes (Student Experience 1.4) | Student Affairs | Outcome |  |  | 2021-07-01
| Create, promote, and emphasize the use of Student Affairs learning outcomes into all co-curricular programming | 4.3 Learning Environment - Learning Outcomes (Student Experience 1.4) | Student Affairs | Strategy | SAAT / SA Departmental Directors | In Progress | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Learning outcomes are integrated by May 2022 | 4.3 Learning Environment - Learning Outcomes (Student Experience 1.4) | Student Affairs | Metric | SAAT / SA Departmental Directors |  |  |  | Staff Time
| Create, promote, and emphasize the use of Student Affairs programs outcomes into all co-curricular planning | 4.3 Learning Environment - Learning Outcomes (Student Experience 1.4) | Student Affairs | Strategy | SAAT / SA Departmental Directors | In Progress | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Programming outcomes are integrated by May 2022 | 4.3 Learning Environment - Learning Outcomes (Student Experience 1.4) | Student Affairs | Metric | SAAT / SA Departmental Directors |  |  |  | Staff Time
| Using Assessment data report out to the University the contributions that the Student Affairs division makes to improving student recruitment, retention and engagement. | 4.4 Learning Environment - Report Assessment Data (Student Experience 1.4) | Student Affairs | Outcome
| Strengthen and improve strategic communication with students, parents and alumni regarding the divisional impact on the student experience at UWSP. | 4.4 Learning Environment - Report Assessment Data (Student Experience 1.4) | Student Affairs | Strategy | Marketing
| Develop and enhance collaborations and partnerships, both internally and externally to collectively promote events and services that improve student recruitment, retention and engagement. | 4.4 Learning Environment - Report Assessment Data (Student Experience 1.4) | Student Affairs | Strategy | Marketing
Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | Align Student Affairs divisional resources (Organizational Structure, Personnel, Facilities, Finances, and Technology) to meet the needs of current and future students. | 5.0 Resources (Finance 1.1) |  | Goal
| Evaluate organizational structure and staffing patterns within Student Affairs to remain relevant to the needs of our current and future populations of students | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Outcome |  |  | 2021-07-01
| VCSA to convene divisional restructuring committee to finalize and implement plan | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy | VCSA / Restructuring Committee / SA Directors | Begun | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Divisional restructing plan drafted by May 2022 for implementation in spring 2023 | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Metric |  |  |  |  | Staff Time
| Look at innovative ways to provide higher level health and wellness prevention and intervention options that are cost effective, adaptable, flexible, and cost effective while meeting the needs of current and future students. | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy
| Design and implement a regular process to review co-curricular programs and services for continued relevance and maintain, enhance or discontinue programs/services based on results. | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy
| Complete cost benefit analysis of options that meet the basic health and wellness needs of current and future students. | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy
| Explore need and viability of expanded childcare offering through UCLCC for after hour and weekend services for post-traditional students to allow parents/car givers to attend college. | 5.1 Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy
| Hire/retain a Student Affairs Grant Writer (Consultant) to explore, and write grants to develop new and expand existing programs and services for students. | 5.01Resources - Organizational Structure/Personnel (Finance 1.1) | Student Affairs | Strategy
Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | Inventory, evaluate and enhance existing while developing new facilities, through effective long-term planning and cost analysis of maintenance, renovations and construction to address flexible, responsive space needs of current and future students, faculty, staff alumni and guests | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Outcome |  |  | 2021-07-01
| Undertake a strategic planning process for facilities that includes a small and large compiled schedule of projects to address routine/deferred maintenance and major renovations or new buildings | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Strategy | Student Affairs Directors / VCSA/ SA Budget Manager | Begun with Housing/UC | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Strategic Plan for facilities completed by May 2022 | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Metric | Student Affairs Directors / VCSA/ SA Budget Manager |  |  |  | Staff Time
| Fund and implement a short-term, long-term, and capital projects to support programs and events for students, faculty, staff, alumni and guest. | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Strategy
| Establish minimal standards for public areas of buildings and bring all public areas up to those standards. | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Strategy
| Plan and implement an award winning Health and Wellness building construction known for its vibrancy, experiential learning efforts and aesthetic appeal. | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Strategy | VCSA / H&W Committee / SA Budget Manager | Begun | 2021-07-01 | 365 | Staff Time and Finances | bar: 2021-07-01 to 2022-06-01
| Health and Wellness committee reconvened to establish new goals and objectives of the project with decisions by April 2022 (BOR). | 5.2 Resources - Facilities (Finance 1.1) | Student Affairs | Metric | VCSA / H&W Committee / SA Budget Manager
Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | Align the fiscal model within Student Affairs to achieve divisional priorities and future vision. | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Outcome |  |  | 2021-07-01
| Create and implement a plan to consolidate and/or reorganize departments/units/programs to meet divisional priorities | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy | VCSA / Restructuring Committee / SA Directors | Begun | 2021-07-01 | 365 | Staff Time | bar: 2021-07-01 to 2022-06-01
| Plan drafted by May 2022 for implementation in spring 2023 | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Metric | VCSA / Restructuring Committee / SA Directors |  |  |  | Staff Time
| Develop a "non-peak-time" space use plan for higher utilization of student affairs programs/services and facilities by community guests | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy
| Explore and develop new strategies for alternative funding sources and revenue enhancements for all Student Affairs departments. | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy
| Implement a bold advancement agenda for the division - Expand strategic partnerships with alumni and major donors to develop a plan for the division to have an annual giving and major gifts week each year. | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy
| Implement a bold advancement agenda for the division - Identify and jointly develop strategic funding priorities for Student Affairs through collaborative planning between student affairs and advancement | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy
| Implement a bold advancement agenda for the division - Develop a strategy to engage students and their families as well as staff and the university community in a manner that elicits a sense of "Paying it Forward." | 5.3 Resources - Finances (Finance 1.1) | Student Affairs | Strategy
Revise the role and mechanisms of course evaluations in order to minimize the effects implicit bias, explicit racism, homophobia, transphobia, sexism, ableism, xenophobia, etc. from students. | Ensure that the division can effectively communicate by providing the most up to date technology and mode of service delivery within all departments. | 5.4 Resources - Technology (Finance 1.1) | Student Affairs / IT | Outcome
| Create a systematic review process of the current technology and delivery modes within all Student Affairs departments | 5.4 Resources - Technology (Finance 1.1) | Student Affairs / IT | Strategy
| Departments to develop a strategic plan to enhance technology and modes of service deliver to meet future program and service needs.. | 5.4 Resources - Technology (Finance 1.1) | Student Affairs / IT | Strategy
| Finance and implement technological strategic plan with the assistance of IT to advance Student Affairs' future initiatives/programs and service delivery. | 5.4 Resources - Technology (Finance 1.1) | Student Affairs / IT | Strategy

## PMP Goal Organization
Purpose Made Possible Goals
We will align University expenditure levels with available resources. Annual expenditure levels in university departments will be within the annual state budget allocation or the program revenue generated. | Finance 1.1
We will utilize financial models that will be data informed, transparent, objective, and action oriented. The financial models will inform decisions to allocate and reallocate resources. | Finance 1.2
We will create ethical processes and metrics to support the financial models and to inform decision-making, resulting in greater transparency and understanding of the current financial situation of the university, the rationale for decision making, and the need to ensure long-term financial sustainability. | Finance 1.3
We will encourage and achieve financial growth. New revenue sources will be explored and analyzed for financial viability. These new revenue sources will complement existing financial resources to allow diversification of university finances. | Finance 1.4
We will increase and expand access by enhancing strategic partnerships with high schools and other educational institutions that support college-bound student success, college completion, and enrollment growth for a diverse student body. | Student Success 1.1
We will grow programs and harness technologies to support post-traditional and graduate learners through creative delivery methods including but not limited to branch campuses, hybrid, online, or collaborative models. This shall involve strengthening student support in terms of course timing/availability, academic calendars, evening/weekend classroom, office and service access, and prior learning experience. | Student Success 1.2
We will develop and implement internal systems and structures to better serve diverse prospective students in our market. The system should use data to determine financial and program viability, and inform new programs/offerings relevant to K-12 traditional, post-traditional, graduate, and continuing ed students. | Student Success 1.3
We will increase our unique cross-disciplinary work to leverage (or promote) our strengths in sustainability, global awareness, and diversity, equity, and inclusion, for prospective students at all credential and continuing education levels. | Student Success 1.4
We will prioritize and expand high-impact practices (HIP) to boost student learning, development, and engagement. | Student Experience 1.1
We will deliver vibrant yet tailored student services that support the retention and success of all students. | Student Experience 1.2
We will build and enhance a community that values inclusion, equity, and diversity. | Student Experience 1.3
We will create an enriched learning environment through the use of advanced evidence-based practices and educational tools, innovative technologies, and equity-minded pedagogies. | Student Experience 1.4
We will collaborate both internally and with community members and organizations to create initiatives that support economic and community development. We will share our stories with each other and our stakeholders and work together to enhance our community. | Communities 1.1
In our internal and external collaborations we will focus on our commitment to be more inclusive and promote equity and diversity. | Communities 1.2
As an educational and cultural resource for the communities we serve, we will develop and promote new types of collaborations that align with the mission of UW-Stevens Point and that lead to greater efficiency, greater opportunity for a UWSP credential, and greater student success through internships and other experiential learning. | Communities 1.3
Build and implment an intentional campus HIP student employment program using learning outcomes and a primary focus on essential skill development | Student Experience 1.1 (a) | Student Affairs | Sub-Strategy
Create a division wide training program for student employees on leadership and management skill development | Student Experience 1.1 (a) | Student Affairs | Sub-Strategy
Develop and Integrate career preparation opportunities that allow students to gain the skills necessary to secure gainful employment in a global marketplace. | Student Experience 1.1 (a) | Student Affairs | Sub-Strategy
Partner with Career and Academic Advising, Financial Aid, Human Resources - Student Payroll Office to increase offerings and viability of career ready workshops to ensure all students successfully market their student employment experiences and skills. | Student Experience 1.1 (a) | Student Affairs | Sub-Strategy

## Sheet1 (hidden)
FY22 | Executive
FY23 | Advancement
FY24 | Marketing & Enrollment
FY25 | Student Affairs
FY26 | Business Affairs
Academic Affairs